## Slide 1: First Phase Report!
Proud Cockroaches team
25/06/2021

## Slide 2: WHOA!
6 days have passed. Congratulations, you have a day off :>
Take a look at our plan, what we’ve done so far and the problems to tackle in the next phase.

## Slide 3: FULL EXPECTED TIMELINE
We did nothing :))))
Mathematical models try-out & data visualization
Start focusing on answering the questions of this problem
Discuss the overall path;
First baby steps to get used to the process
Get to finish the whole project
Prepare all documents and the final report file
from the start to 19/06
20/06 – 25/06
26/06 – 01/07
02/07 – 07/07
and the last 3 days is, you know, for ambulance situations....
25/06 – 26-06: day off
01/07 – 02-07: day off
Note: I assume that everyday starts at noon; that’s why I denoted the day off as: (noon of) 25/06 to (noon of) 26/06. Thus, that is 1 day, not 2 days :P

## Slide 4: WHAT WE’VE DONE SO FAR
Only the basics, but useful enough.
Learn to use spss
It’s a lot, to be honest. You guys are GREAT.
retrieve the data
Need to dig through “every corner of the Internet”, LOL. Just kidding, but honestly it was time-consuming and really confused.
data cleaning
Check, then filter the required entries, make separate datasets for every country... A whole bunch of time went into that process!
Learn to use google colab
What an amazing toolset for developing in Python language.
learn to use python ml syntaxes
learn about “model evaluation metrics”
Though not so many and mostly copied from the Internet, I’m still proud of it. You can, too.
RMS, MSE, RMSE, MAE, MAPE, RMSLE (???) Mind blown....
found the path for this assignment
Ever wondered why we did nothing in the first 20 days? Because of this!!!! We need a path to follow, and luckily, we found it (presented in the first ever team meeting).

## Slide 5: APPRoXIMATE DONE PERCENTAGES
So far, all the things we know about forecasting models are limited. Need more work.
model
We still have some more criteria to add to the dataset, and visualization step.
data
30%
15%

## Slide 6: CURRENT PROBLEMS/LACKINGS
Yep. You read the title.
What a shame :<
3. NOT YET DECIDING WHICH OTHER CRITERIA TO CALCULATE OTHER THAN CONFIRMED, DEATH AND RECOVERED
1. NOT YET DECIDING WHAT WE WANT TO PREDICT
We need a set of questions to build visualzations and models based on it.
2. NOT YET HAVING A QUESTION SET
4. NOT YET UNDERSTANDING PYTHON MODELS SYNTAXES
Though we mostly know nothing about Python, I think it is quite easy to catch up. For this project, you don’t need to study Python from scratch. The syntaxes are quite understandable.

## Slide 7: THE NEXT PHASE: 26/06 – 01/07
In this phase, we need to tackle the remaining problems in the previous slide, and of course, conquer new challenges!

## Slide 8: THANKS LMAO